## MVP Tracker
Priority | Phase | Task | Owner | Status | Account Required | Dependency | Deliverable | Notes
P0 | Foundation | Confirm product scope | ChatGPT/User | Done | No |  | 5 screens + Seoul seed
P0 | Foundation | Initial 50-place seed DB | ChatGPT | Done | No |  | data/seed_data.json
P0 | Foundation | Supabase schema + RLS | ChatGPT | Done | No |  | supabase/01_schema.sql
P0 | Foundation | Seed SQL | ChatGPT | Done | No | Supabase schema | supabase/02_seed_seoul50.sql
P0 | Foundation | Storage policy | ChatGPT | Done | No | Supabase schema | supabase/03_storage.sql
P0 | Foundation | FlutterFlow helper RPC | ChatGPT | Done | No | Supabase schema | supabase/04_flutterflow_rpc.sql
P0 | Prototype | Clickable mobile prototype | ChatGPT | Done | No | Seed DB | prototype/single_file_prototype.html
P0 | Prototype | Home interaction | ChatGPT | Done | No | Prototype | Home working
P0 | Prototype | Place detail dynamic template | ChatGPT | Done | No | Prototype | Detail working
P0 | Prototype | Curation detail | ChatGPT | Done | No | Prototype | 6 curations working
P0 | Prototype | Save/Visited local prototype | ChatGPT | Done | No | Prototype | localStorage working
P0 | Data | Verify 50 addresses | User/ChatGPT | In progress | No | Seed DB | verified addresses | Manual review for ambiguous sites
P0 | Data | Geocode 50 places | User/ChatGPT | Blocked | Yes | Verified addresses | lat/lng in Supabase | Needs map/geocoding provider
P0 | Data | Re-verify current operation/programs | User/ChatGPT | In progress | No | Seed DB | current status | Refresh before launch
P0 | Media | Select launch photo policy | User | Todo | No |  | rights policy
P0 | Media | Secure cover images for MVP A | User | Todo | No | Photo policy | 20+ licensed covers
P0 | Media | Populate media copyright metadata | User/ChatGPT | Todo | No | Licensed images | media rows
P0 | Supabase | Create Supabase account/project | User | Blocked | Yes |  | Project
P0 | Supabase | Run 01_schema.sql | User/ChatGPT | Blocked | Yes | Supabase project | DB schema
P0 | Supabase | Run 02_seed_seoul50.sql | User/ChatGPT | Blocked | Yes | Schema | 50 places loaded
P0 | Supabase | Run 03_storage.sql | User/ChatGPT | Blocked | Yes | Schema | bucket/policy
P0 | Supabase | Run 04_flutterflow_rpc.sql | User/ChatGPT | Blocked | Yes | Schema | RPCs
P0 | Supabase | Run audit/smoke tests | User/ChatGPT | Blocked | Yes | Seed loaded | QA report
P0 | FlutterFlow | Create FlutterFlow project | User | Blocked | Yes |  | Project
P0 | FlutterFlow | Connect Supabase OAuth/Get Schema | User/ChatGPT | Blocked | Yes | Both projects | Schema visible
P0 | FlutterFlow | Set theme tokens | User/ChatGPT | Blocked | Yes | FF project | Theme
P0 | FlutterFlow | Build reusable components | User/ChatGPT | Blocked | Yes | Theme | Components
P0 | FlutterFlow | Build HomePage | User/ChatGPT | Blocked | Yes | Components | Home
P0 | FlutterFlow | Build PlaceDetailPage | User/ChatGPT | Blocked | Yes | Home | Detail
P0 | FlutterFlow | Build Curation pages | User/ChatGPT | Blocked | Yes | Components | Curation
P0 | Maps | Create Google Cloud project/API keys | User | Blocked | Yes |  | Maps keys
P0 | Maps | Apply API key restrictions | User/ChatGPT | Blocked | Yes | Maps keys | restricted keys
P0 | Maps | Build MapPage | User/ChatGPT | Blocked | Yes | Geocoding + Maps keys | Map
P0 | Auth | Enable Supabase Auth | User/ChatGPT | Blocked | Yes | Supabase/FF | Auth
P0 | Auth | Save toggle production | User/ChatGPT | Blocked | Yes | Auth/RPC | Saved
P0 | Auth | Visited production | User/ChatGPT | Blocked | Yes | Auth/RPC | Visited
P0 | FlutterFlow | Build My Light Map | User/ChatGPT | Blocked | Yes | Auth + Maps | My
P1 | Search | Connect search_places RPC | User/ChatGPT | Blocked | Yes | Supabase/FF | Search
P1 | Release | Privacy policy finalization | User | Todo | No | Operating entity | Policy URL
P1 | Release | Support email / URL | User | Todo | No |  | Support info
P1 | QA | Run QA test suite | User/ChatGPT | Blocked | Yes | App build | QA pass
P1 | QA | Android real-device test | User | Blocked | Yes | App build | Device QA
P1 | QA | iOS TestFlight test | User | Blocked | Yes | Apple account/build | Device QA
P1 | Release | Store screenshots | User/ChatGPT | Blocked | Yes | Final UI | Screenshots
P1 | Release | Google Play submission | User | Blocked | Yes | Play account | Release
P1 | Release | Apple App Store submission | User | Blocked | Yes | Apple Developer | Release

## Summary
빛의 건축 v0.1 | 구현 준비도
Metric | Value
Total tasks | 46
Done | 11
In progress | 2
Blocked (account/dependency) | 28
Account Gate | Status
Supabase | Not created
FlutterFlow | Not created
Google Maps API | Not created

## Place Readiness
place_code | name_kr | category | district | verification | priority | geocode_status | Coordinates | Image rights | Current program QA | Launch ready
SEOUL001 | 아뜰리에 노들 | Media Facade | 용산구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL002 | 아뜰리에 광화 | Media Facade | 종로구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL003 | 해치마당 미디어월 | Media Art | 종로구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL004 | 오간수교 미디어파사드 | Media Facade | 종로구/중구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL005 | 서울로미디어캔버스 | Media Art | 중구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL006 | 동대문디자인플라자(DDP) / 서울라이트 | Media Facade | 중구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL007 | 코엑스 K-POP 스퀘어 WAVE | Media Facade | 강남구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL008 | 신세계스퀘어 | Media Facade | 중구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL009 | 갤러리아 명품관 WEST 미디어파사드 | Media Facade | 강남구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL010 | 서울스퀘어 미디어 캔버스 | Media Facade | 중구 | medium | A | needs_geocoding | Missing | Pending | Review | NOT READY
SEOUL011 | KT스퀘어 옥외전광판 | Media Facade | 종로구 | high | B | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL012 | K-비전(코리아나호텔) | Media Facade | 중구 | high | B | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL013 | 루미 미디어(세광빌딩) | Media Facade | 종로구/중구 | high | B | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL014 | LUUX(동아일보) | Media Facade | 종로구 | high | B | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL015 | 일민미술관 옥외전광판 | Media Facade | 종로구 | high | B | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL016 | 서울로봇인공지능과학관 미디어파사드 | Media Facade | 도봉구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL017 | 마곡 르웨스트 미디어파사드 | Media Facade | 강서구 | medium | B | needs_manual_review | Missing | Pending | Review | NOT READY
SEOUL018 | 롯데월드타워 미디어파사드 | Media Facade | 송파구 | medium | A | needs_geocoding | Missing | Pending | Review | NOT READY
SEOUL019 | 롯데타운 라이트(영플라자) | Media Facade | 중구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL020 | 하이커 그라운드 | Media Art | 중구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL021 | 청계 소울 오션 | Immersive | 중구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL022 | 국립중앙박물관 디지털 실감 영상관 | Immersive | 용산구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL023 | 라이트룸 서울 | Immersive | 강동구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL024 | 서울시립 서서울미술관 | Media Art | 금천구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL025 | 국립현대미술관 서울 | Media Art | 종로구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL026 | 아트센터 나비 | Media Art | 종로구 | medium | A | needs_manual_review | Missing | Pending | Review | NOT READY
SEOUL027 | 리움미술관 | Media Art | 용산구 | high | B | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL028 | 디뮤지엄 | Media Art | 성동구 | medium | B | needs_geocoding | Missing | Pending | Review | NOT READY
SEOUL029 | 플랫폼엘 컨템포러리 아트센터 | Media Art | 강남구 | high | B | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL030 | 스페이스K 서울 | Media Art | 강서구 | medium | B | needs_geocoding | Missing | Pending | Review | NOT READY
SEOUL031 | 문화역서울284 | Media Art | 중구 | medium | B | needs_geocoding | Missing | Pending | Review | NOT READY
SEOUL032 | 서울도시건축전시관 | Media Art | 중구 | medium | B | needs_geocoding | Missing | Pending | Review | NOT READY
SEOUL033 | 문화비축기지 T4·T5 | Immersive | 마포구 | high | B | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL034 | 서울시립 사진미술관 | Media Art | 도봉구 | high | B | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL035 | 서울시립미술관 서소문본관 | Media Art | 중구 | high | B | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL036 | 서울시립 북서울미술관 | Media Art | 노원구 | high | B | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL037 | 서울시립 백남준을 기억하는 집 | Media Art | 종로구 | high | B | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL038 | 서울시청 서울림(林) 미디어월 | Media Art | 중구 | high | B | needs_geocoding | Missing | Pending | Review | NOT READY
SEOUL039 | 피크닉 | Media Art | 중구 | medium | B | needs_geocoding | Missing | Pending | Review | NOT READY
SEOUL040 | 더현대 서울 ALT.1 | Immersive | 영등포구 | medium | B | needs_geocoding | Missing | Pending | Review | NOT READY
SEOUL041 | 그라운드시소 이스트 | Immersive | 광진구 | medium | B | needs_manual_review | Missing | Pending | Review | NOT READY
SEOUL042 | 그라운드시소 서촌 | Media Art | 종로구 | medium | C | needs_geocoding | Missing | Pending | Review | NOT READY
SEOUL043 | N서울타워 | Light Art | 용산구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL044 | 세빛섬 | Light Art | 서초구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL045 | 반포대교 달빛무지개분수 | Light Art | 서초구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL046 | 서울로7017 야간조명 | Light Art | 중구 | high | B | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL047 | 홍제유연 | Light Art | 서대문구 | medium | A | needs_geocoding | Missing | Pending | Review | NOT READY
SEOUL048 | 별마당도서관 | Architecture | 강남구 | high | B | needs_geocoding | Missing | Pending | OK | NOT READY
SEOUL049 | 서울웨이브 아트센터 | Architecture | 서초구 | medium | C | needs_geocoding | Missing | Pending | Review | NOT READY
SEOUL050 | 노원 불빛정원(화랑대 철도공원) | Light Art | 노원구 | high | A | needs_geocoding | Missing | Pending | OK | NOT READY

## QA
id | area | test | steps | expected | priority | status
QA-001 | Public | Home anonymous | 로그아웃 상태 앱 실행 | Home이 로그인 없이 로드 | P0 | Not run
QA-002 | Data | Seed count | Supabase places 조회 | 50행 존재 | P0 | Not run
QA-003 | Navigation | Place detail | Home 카드 탭 | 선택한 placeId의 상세정보 표시 | P0 | Not run
QA-004 | Search | Korean search | '광화' 검색 | 관련 장소 반환 | P1 | Not run
QA-005 | Curation | Curation order | 큐레이션 상세 진입 | sort_order 순으로 장소 표시 | P1 | Not run
QA-006 | Auth | Login gate | 로그아웃 상태 저장 탭 | Auth 화면으로 이동 | P0 | Not run
QA-007 | Save | Toggle save | 로그인 후 저장 2회 | insert 후 delete; 중복행 없음 | P0 | Not run
QA-008 | Visit | Visit counter | 방문했어요 2회 | visit_count가 2 | P1 | Not run
QA-009 | RLS | Cross-user saved | 사용자 B로 사용자 A 데이터 접근 시도 | 읽기 불가 | P0 | Not run
QA-010 | RLS | Cross-user visited | 사용자 B로 사용자 A 데이터 접근 시도 | 읽기 불가 | P0 | Not run
QA-011 | Map | Missing coordinate safety | lat/lng null 장소 존재 | 지도 marker로 전달되지 않음 | P0 | Not run
QA-012 | Map | Coordinate bounds | 모든 좌표 검사 | lat -90~90, lng -180~180 | P0 | Not run
QA-013 | External | Official URL | 상세 공식링크 탭 | 정상 URL 열림 | P1 | Not run
QA-014 | Copyright | Media metadata | 이미지 게시 전 확인 | copyright/source 기록 | P0 | Not run
QA-015 | My | Stats | 저장/방문 후 My 진입 | KPI가 실제 데이터와 일치 | P1 | Not run
QA-016 | Responsive | Galaxy | Android 실기기 확인 | 텍스트 잘림/오버플로 없음 | P1 | Not run
QA-017 | Accessibility | Text scale | 폰트 확대 | 핵심 CTA 사용 가능 | P2 | Not run
QA-018 | Offline | Prototype localStorage | 프로토타입 저장/방문 후 새로고침 | 기록 유지 | P2 | Not run